# INTOSAI-Donor Cooperation Work Plan 2013

| No. | Theme and Task | Priority for 2013 | Responsibility | Responsibility within the Secretariat | Deadline |
| --- | --- | --- | --- | --- | --- |
| 1 | INTOSAI-Donor Cooperation Management |  |  |  |  |
| 1.1 | Facilitate SC meeting and SC leadership teleconferences | High | Secretariat |  | Continuous |
|  | SC Meeting China |  |  | Merethe (Einar) |  |
|  | Website, publication and I-D Dictonary |  |  | Merethe (Einar) |  |
| 1.2 | Communication and outreach on INTOSAI-Donor Cooperation (inc. newsletters) | High | Secretariat |  | Continuous |
|  | Newsletter |  |  | Silje (Merethe) |  |
|  | Outreach |  |  | All (Einar) |  |
|  | New signatories |  |  | Einar |  |
| 2 | Funding Mechanisms and Project Identification |  |  |  |  |
| 2.1 | Secure pledges for and establish SAI Capacity Development Fund | High | Donors and Secretariat | Martin (Silje) | ASAP |
| 2.2 | Launch 2nd Global Call for Proposals | High | Secretariat | Silje (Meike) | TBC |
|  | Review proposals |  |  | All participate. Silje (Meike) |  |
| 2.3 | Prepare and submit concept notes | High | INTOSAI applicants, Secretariat |  | TBC |
| 2.4 | Develop full proposals and match to funding | High | INTOSAI applicants, World Bank, Secretariat |  | TBC |
| 3 | SAI Performance Measurement Framework |  |  | Martin (Meike and Silje). All involved. |  |
| 3.1 | Exposure draft SAI PMF published on WGVBS website | High | SAI PMF Task Team |  | April |
| 3.2 | Training courses for assessors run in all INTOSAI regions | High | SAI PMF Task Team |  | June |
| 3.3 | Phase 2 pilots in progress | High | SAIs, INTOSAI bodies, donors |  | Continuous |
| 3.4 | Exposure draft SAI PMF presented at 6th SC meeting and INCOSAI XXI | High | SAI PMF Task Team |  | October |
| 4 | Knowledge Centre on Support to SAIs |  |  |  |  |
| 4.1 | Maintenance of SAI capacity development database | High | Secretariat | Merethe (Silje) | Continuous |
| 4.2 | Disseminate public goods, support to donor engagement with SAIs, represent INTOSAI in development fora | Medium | Secretariat | All | Continuous |
| 4.3 | Training for donors on working with SAIs - Training material drafted - Pilot training course completed - Proposal for roll-out completed | Medium | Secretariat | Meike (Martin) | - March - June - October |
| 4.4 | Training for SAIs on engagement with donors and writing funding applications | Medium | Secretariat | Silje (Meike) | TBC – linked to timing of Global Call for Proposals |
| 5 | Strengthening the Supply of Support to SAIs |  |  |  |  |
| 5.1 | - Establish SAI Supply Side Community of Practice - Hold first technical update | Medium | Secretariat | Meike (Martin) | - July - December |
| 5.2 | Develop guidance on better evaluations of SAI capacity development projects - Terms of reference approved | Medium | Secretariat, SAI Sweden & SAI Norway | Martin (Silje) | - September |
| 6 | SAI Research Agenda |  |  |  |  |
| 6.1 | SAI involvement in audit of extractive industries – mapping and way forward | Low | Secretariat with AFROSAI-E | Meike and Silje | April |
| 6.2 | Benchmarking of SAI funding levels - Decision on inclusion in possible 2013 stock taking, and way forward | Low | Secretariat | Meike (Silje) | TBC, subject to progress on INTOSAI Information Database |
|  | Civil Society participation in audits/Communication with OECD-DAC |  |  | Meike (Silje) |  |
| 7 | Monitoring and Evaluation |  |  |  |  |
| 7.1 | Annual progress report | High | Secretariat | Martin and Einar | May |
| 7.2 | Stock taking update - Decision on added value from possible 2013 stocktaking, and way forward | Medium | Secretariat | Ask SC Leadership in March whether this should be done in 2013/2014 | TBC, subject to progress on INTOSAI Information Database |
| 7.3 | External evaluation of IDI | Medium | IDI | Einar | June |