INTOSAI-Donor Cooperation Work Plan 2014

| No | Theme and Task | Priority 2014 | Responsibility | Deadline |
| --- | --- | --- | --- | --- |
| 1 | INTOSAI-Donor Cooperation Management |  |  |  |
| 1.1 | Facilitate SC meeting and SC leadership teleconferences | High | Secretariat | Continuous |
| 1.2 | Communication and outreach on INTOSAI-Donor Cooperation (inc. newsletters) | High | Secretariat | Continuous |
| 2 | Funding Mechanisms and Project Identification |  |  |  |
| 2.1 | Prepare and submit draft concept notes for GCP | High | INTOSAI applicants | 31 January |
| 2.2 | Feedback on draft concept notes | High | Secretariat | 28 February |
| 2.3 | Prepare and submit final concept notes | High | INTOSAI applicants | 31 March |
| 2.4 | Translated concept notes shared with donors and SAI providers of support | High | Secretariat | 30 April |
| 2.5 | Donors and SAI providers of support express initial interest in concept notes | High | Donors and SAI providers of support | June* |
| 2.6 | Develop full proposals and match to funding | High | INTOSAI applicants, World Bank, Secretariat | June onwards |
| 2.7 | Secure pledges for and establish SAI Capacity Development Fund | High | Donors, World Bank and Secretariat | ASAP |
| 2.8 | Reporting on progress under GCP11 | High | Secretariat | Continuous |
| 3 | SAI Performance Measurement Framework |  |  |  |
| 3.1 | Regional training courses for assessors provided on demand | High | Secretariat & SAI PMF facilitators | Continuous |
| 3.2 | Support and monitor progress of phase 2 pilots | High | Secretariat | Continuous |
| 4 | Knowledge Centre on Support to SAIs |  |  |  |
| 4.1 | Maintenance of SAI capacity development database | High | Secretariat | Continuous |
| 4.2 | Disseminate public goods, support donor engagement with SAIs | Medium | Secretariat | Continuous |
| 4.3 | Represent INTOSAI in development fora | Medium | CBC Chair and Secretariat | Continuous |
| 4.4 | Training for donors on working with SAIs - Pilot training course delivered - Updated course outline to SC - E-learning version launched | Medium | Secretariat | - March - June * - After pilot |
| 5 | Strengthening the Supply of Support to SAIs |  |  |  |
| 5.1 | SAI supply side - Agreement on way forward with CBC - Present challenges in SAI supply side to SC | Low | Secretariat, CBC & others | - June * - June * |
| 5.2 | Develop guidance on better evaluations of SAI capacity development projects - Establish project structure & agree approach - Guidance drafted and ready for piloting | Low | Secretariat, SAI Sweden & SAI Norway | - January - December |
| 6 | SAI Research Agenda |  |  |  |
| 6.1 | Citizen engagement and SAIs: stock take | Low | OECD, SAI Brazil, SAI Chile, SAI South Africa | TBC |
| 6.2 | Benchmarking of SAI funding levels: Initial data analysis based on IDI Global Survey Results | Medium | Secretariat | June* |
| 6.3 | Issue calls for, and manage, SAI research proposals | Low | Secretariat | June* |
| 7 | Monitoring and Evaluation |  |  |  |
| 7.1 | Secretariat annual progress report to funders | High | Secretariat | May |
| 7.2 | Global SAI Monitoring Report, based on IDI Global Survey Results | Medium | IDI | June* |
| 7.3 | Synthesis of SAI Project Evaluations | Medium | Secretariat | June* |
| 7.4 | INTOSAI-Donor Cooperation Impact Assessment - Terms of reference approved - Evaluator Commissioned - Inception report | High | - Steering Committee - SC leadership/Secretariat - Evaluator | - June* - August - October |

* Timing linked to 7th SC meeting