Supreme Audit Institutions Capacity Development Fund (SAI CDF)

Operating Manual

Approved by the Funding Board (March 2015)

Table of Contents

Section 1: Background

Section 2: SAI Capacity Development Fund (CDF)

A: Purpose and Objectives of the SAI CDF

B: Eligible Beneficiaries

C: Eligible Activities

D: Ineligible Activities

E: Duration of the SAI CDF

F: Legal Considerations

G: Governance Arrangements for the SAI CDF

H: Reporting to the Donor at the Trust Fund Level

Section 3: CDF Grants

I: Project Preparation and Approval Process

J: Criteria for evaluating Project Concept Notes

K: Grant Amount, Duration, and Co-financing

L: Grant Eligible Expenditures

M: Grant Agreements

N: Grant - Project Reporting

O: Grant Implementation Supervision

Section 4: Relationship with the INTOSAI-Donor Cooperation

Annexes

Annex 1: SAI Capacity Development Fund (SAI CDF) – LOGFRAME

Annex 2: SAI Capacity Development Fund – List of Eligible Beneficiaries

Annex 3: Project Concept Note Template

Annex 4: Criteria for the Evaluation of Project Concept Notes

Annex 5: Project Concept Note – Logframe Template

Section 1: Background

- The Memorandum of Understanding (MoU) signed between the International Organization of Supreme Audit Institutions (INTOSAI) and 22 Donor Agencies recognizes the potential value of Supreme Audit Institutions (SAIs) in strengthening governance, accountability and poverty reduction. Accordingly, it seeks to augment and strengthen support to SAIs in developing countries.

- In the MoU, the Donor Community declares its commitment, in accordance with its respective rules, laws, and procedures, to delivering financial or other support for capacity building programs in a harmonized and coordinated manner. The MoU recognizes multiple modalities for donor funding, including but not limited to trust fund or pooled funding arrangement.

- The INTOSAI-Donor Cooperation seeks to ensure that all capacity development support to SAIs, regardless of delivery and financing mechanism, is built on the following principles:

- SAI leadership, ownership and strategic planning, including through developing and implementing Strategic and Development Action Plans

- Support aligned behind SAI-led Strategic and Development Action Plans, harmonized between providers, and coordinated with existing support

- A focus on delivering results that demonstrate improvements in SAI performance

- At the second meeting of the INTOSAI-Donor Cooperation Steering Committee, it was agreed in principle to establish a pooled fund as a complement to other funding modalities. A pooled fund was considered to add value to the INTOSAI-Donor Cooperation by increasing the support to SAIs in developing countries, increasing coordination among donors, strengthening the focus on SAIs’ strategic and development plans, reducing transaction costs for SAIs and donors, and contributing to improved allocation of support. The INTOSAI-Donor Cooperation Secretariat explored options and presented a discussion paper at the third meeting of the Steering Committee, where a decision was made to establish a task force of like-minded donors to develop and establish a mechanism for pooled funding.

- The Task Force agreed on the basic elements (“term sheet”) that would govern a pooled fund and requested the World Bank to prepare, on that basis, draft operating arrangements that –once discussed and agreed with the Contributing Donors– would underpin a potential Multi-Donor Trust Fund administered by the World Bank for a Supreme Audit Institution Capacity Development Fund (SAI CDF).

- This document presents operating arrangements, as adopted at the 16th March 2015 meeting of the Funding Board. It should be clarified that a number of requirements included in this manual are also reflected in the TF Administration Agreement.

Section 2: SAI Capacity Development Fund

- Purpose and Objectives of the SAI CDF

- Purpose of the SAI CDF - The purpose of the SAI CDF is to strengthen governance and public financial management in developing countries, through direct capacity development support to SAIs and to INTOSAI global and regional bodies.

- Objectives of the SAI CDF - The SAI CDF aims to contribute to the effective implementation of the INTOSAI-Donor Cooperation (Cooperation) MoU. Global outcomes of the Cooperation are monitored and evaluated at that level. In the interest of harmonization, the objectives of the SAI CDF are consistent with the outcomes of the overall INTOSAI-Donor Cooperation.

- The SAI CDF has the following specific objectives:

- Scale up support for SAI Capacity Development in developing countries, by providing a sound and streamlined vehicle for donors to fund improvements in SAI performance

- Enhance the effectiveness of support to SAIs, by

  - Improving  allocative efficiency of funding for SAI capacity development, by ensuring resources flow to the areas where they are most needed and can have the greatest impact

  - Strengthening SAI leadership and ownership of capacity development, by providing funding for and incentivizing the development and implementation of SAIs’ Strategic and Development Action Plans.

  - Strengthening donor harmonization and alignment behind SAI-led Strategic and Development Action Plans

  - Improving donor coordination in support to SAIs, by establishing a multi-donor vehicle for funding and decision making on provision of support

  - Reducing the transaction costs for both SAIs and Donors, through developing a single, tailored and streamlined set of procedures for funding SAI capacity development

- Deliver results through financing and managing SAI capacity development programs, with a focus on achieving improvements in SAI performance

- A logframe for the SAI CDF, capturing global outcomes and specific outputs, is presented in Annex 1. The logframe will be kept flexible, with periodic updates made as deemed necessary by the SAI CDF Funding Board.

- Eligible Beneficiaries

- The following organizations/institutions/bodies are eligible to receive support from the SAI CDF provided they are eligible to enter into financing agreements with the World Bank.

- SAIs of countries or territories on the DAC list of ODA eligible recipients which are able to enter into agreements with the World Bank – See Annex 2 (e.g. IBRD members plus the Palestinian Administered Areas). Proposals from SAIs of all countries or territories on the DAC list of ODA eligible recipients are eligible for consideration for funding from the CDF from the point of notification to the Funding Board and/or the CDF Program Manager of their intention to submit a proposal;

- INTOSAI regional and sub-regional bodies whose activities are wholly or predominantly ODA eligible, or for specific activities undertaken by INTOSAI regional or sub-regional bodies and considered wholly or predominantly ODA eligible; and

- INTOSAI Global and Trans-regional bodies (including the work of INTOSAI committees, sub-committees, working groups and task forces), for activities undertaken predominantly for the benefit of SAIs under point (a) above. Funding for global activities, including the development of global public goods, should demonstrate the potential benefit and likely take up by SAIs under point (a) above.

- Eligible Activities

- All expenditures financed by CDF will be in support of activities designed to contribute to capacity development of SAIs. Capacity development is the sustained development of the core capabilities of an SAI to deliver its mandate more effectively so as to create the desired impact. It implies strengthening the institutional framework within which the SAI operates, the organizational systems within the SAI, and the professional capacity of its management and staff.

- Specifically the following capacity development activities are eligible for support:

- Organizational capacity development: Refers to the legal framework within which the SAI operates, to the managerial competencies, and instruments that help determine the degree to which the SAI/Region can operate effectively. (e.g. strategic plans, strategic development, annual planning, financial resource planning, professional staff development, ability to manage outsourcing of audit work, ability to manage inward capacity development assistance, quality control systems, internal controls, and infrastructure)

- Financial audit capacity development: Refers to an independent assessment, resulting in a reasonable assurance opinion, of whether an entity’s reported financial condition, results, and use of resources are presented fairly in accordance with the financial reporting framework. (e.g. adoption of ISSAIs on financial auditing, on the job training in financial auditing, training programmes, implementation of computerized audit tools, and joint audits)

- Compliance audit capacity development: deals with the degree to which the audited entity follows rules, laws and regulation, policies, established codes, or agreed upon terms and conditions, etc. Compliance auditing may cover a wide range of subject matters. In general, the purpose of a compliance audit is to provide assurance to intended users about the outcome of the evaluation or measurement of a subject matter against suitable criteria. (e.g. adoption of ISSAIs on compliance auditing, training programs, development of SAI specific compliance audit guidance material, and pilot audits)

- Performance audit capacity development: refers to an audit of the economy, efficiency and effectiveness with which the audited entity uses its resources in carrying out its responsibilities. Also known as Value for Money audit. (e.g. development of standards and guidance material on performance auditing, training in data analysis and report writing, and peer reviews on performance auditing)

- IT audit capacity development: the process of collecting and evaluating evidence to determine whether a computer system has been designed to maintain data integrity, safeguard assets, allows organisational goals to be achieved effectively, and uses resources efficiently. (e.g. development of guidance material/standards on IT audit, SAI training on IT audit, and professional qualifications in IT auditing)

- Other specialized audit capacity development: refers to all audits carried out other than financial, compliance, performance and IT audit. (e.g. environmental audit, investigation of fraud and corruption/forensic audit)

- Administrative services capacity development: defined as all tasks, other than auditing, that contributes to the day-to-day operations of the SAI. (e.g. human resource management, IT services, knowledge & learning function, accounts, and information and other administrative services)

- External stakeholders’ relation capacity development: refers to the practice of managing communication between a SAI and its stakeholders. (e.g. reporting, media management, public relations, communication with Parliament and Public Accounts Committee, and communication with civil society and other stakeholders)

- Ineligible Activities

- Activities that are ineligible for SAI CDF funding include:

- Meeting basic expenditure needs, such as payment of regular salaries and wages, utility (water/heat/electricity) expenses, maintenance expenses;

- Travel expenses unrelated to the program defined in the project proposal;

- Purchase of motor vehicles

- Duration of the SAI CDF

- The SAI CDF will become effective upon signing of the first Trust Fund Administration Agreement, and operate until such time as the signatories agree to wind-up the Fund.

- Legal Considerations

- The Programmatic Trust Fund (TF) is governed by the Administration Agreements and the Grant Agreements.

- Trust Fund Administration Agreements are entered between each contributing Donor and the World Bank. The TFAAs specify the TF’s purposes and scope of activities to be financed; and the arrangements governing the use of funds, progress and financial reporting, fee arrangements, auditing, and disclosure of information, among others. The World Bank designates a Program Manager (PM) to oversee implementation of the program-specific activities provided for in the administration agreements.

- Contributing Donors make financial contributions to the SAI CDF in accordance with the value, schedule and other terms of the TF Administration Agreement.

- In Multi-Donor Trust Funds administered by the World Bank, contributing Donors may state a non-binding preference that their contributions be used to finance one or more geographical components, but without a legally binding commitment by the Bank to earmark funds by individual participating donors to specific activities or to specific recipients.

- The World Bank will maintain separate records and ledger accounts in respect of the contributions deposited in the Trust Fund account and disbursements made therefrom, and will provide contributing donors with current financial information relating to receipts, disbursements and fund balance in the holding currency of the Trust Fund with respect to the Contributions.

- The World Bank will provide to the contributing donors, within six months following the end of each Bank fiscal year, an annual single audit report, comprising (a) management assertion together with an attestation from the Bank’s external auditors concerning the adequacy of internal control over cash-based financial reporting for all cash-based trust funds as a whole; and (b) combined financial statement for all cash-based trust funds together with the external auditor’s opinion thereon

- The CDF Administration, Program Management and grant implementation supervision will be governed by the following cost considerations:

- TF administration and related expenses 2% of each contribution

- Program management costs 5% of each contribution (estimated on a full cost recovery basis and charged on an actual basis)

- Technical and fiduciary supervision of recipient-executed grants/activities at 8% of the grant amount (estimated on a full cost recovery basis, and charged on an actual basis)

- Governance Arrangements for the SAI CDF

- A Funding Board, comprised of representatives from all organizations contributing to the SAI CDF (“Contributing Donors”), as well as the World Bank, will serve as the supreme governance body of the fund. The Funding Board will be chaired by the Chief Financial Management Officer in the Operations Policy and Country Services vice presidency of the World Bank.

- The Funding Board will have the following responsibilities:

- Approve and if necessary modify the SAI CDF Operating Manual

- Approve and if necessary modify the SAI CDF  Allocation Criteria

- Enter into agreement with the INTOSAI-Donor Secretariat as regards the Secretariat’s role in conducting a preliminary review, if any, of the short proposals received under the INTOSAI-Donor Cooperation’s Global Call for Proposals

- Approve or reject funding for Project Concept Notes in line with the available funding and the Allocation Criteria

- Approve the annual work program (i.e. plan of administrative tasks including monitoring and evaluation activities) prepared by the Program Manager (PM)

- Review periodic progress reports prepared by the PM

- Ensure appropriate monitoring of the SAI CDF as a whole and conduct a mid-term review of the CDF. The main objective of the mid-term review would be to review the focus of the ongoing CDF funded activities with regard to the purpose and expected outcomes of the CDF and to review the processes used for the selection and management of the activities. The timing of the mid-term review will be approved by the Funding Board.

- Commission an evaluation of the SAI CDF at the appropriate time (the scope, timing, and conduct of such evaluation will be agreed with the World Bank)

- The following procedures will govern the meetings of the Funding Board:

- The Funding Board will meet (in person or virtually) at least once every year and more regularly if required for the timely approval of funding proposals, and approval of work programs and progress reports. Where possible, the Funding Board will meet in person in connection with meetings of the Steering Committee. Minutes will be kept of each Funding Board meeting.

- Observers and experts could be invited to Funding Board meetings with the permission of the Chair, subject to advance notification to the Funding Board.

- The PM will be responsible for arranging meeting schedules, facilitating meetings and virtual reviews, and drafting minutes. The PM may convene extraordinary meetings of the Funding Board, as needed.

- The decision making at the FB meetings will be guided by the following principles :

- Decisions are reached through consensus during the Funding Board meetings or via email correspondence.

- For decisions that are made via email, a proposal is sent by the PM to the Funding Board members with a date specified for comment. If a Funding Board member does not reply or does not request an extension within that specified time period, that member’s agreement is deemed to have been received.

- Roles and responsibilities of the World Bank as the Trustee and Program Manager of the SAI CDF:

- Trust Fund administration activities in accordance with the TF Administration Agreements, including receiving, holding, investing, disbursing and reporting on funds.

- Program management activities coordinated by the PM, including:

  - Providing support to the Funding Board

  - Preparation of annual work programs

  - Receipt of short proposals from the INTOSAI-Donor Secretariat under the Global Call for Proposals including results of the preliminary review conducted by the  INTOSAI-Donor Secretariat

  - Managing the process for getting Project Concept Notes from the colleagues within the WB

  - Detailed review of Project Concept Notes for consideration of the Funding Board

  - Progress reporting to the Contributing Donors on the activities financed by the contributions

  - Awareness raising and external communications on the SAI CDF objective, including dialogue with potential donors to the CDF.

  - Updating the SAI Capacity Development Database maintained by the Cooperation Secretariat

- Grant preparation and supervision activities coordinated by each grant TTL, including:

  - Appraising projects to be financed by Recipient-executed grants

  - Entering into grant agreements with Recipients

  - Supervision and monitoring of Recipient-executed activities

- Reporting to the Donor at the Trust Fund Level

- The Bank shall furnish to the Donors current financial information relating to receipts, disbursements and fund balance in the Holding Currency with respect to the Contributions via the World Bank’s Trust Funds Donor Center secure website.  Within six (6) months after all commitments and liabilities under the Trust Fund have been satisfied and the Trust Fund has been closed, the final financial information relating to receipts, disbursements and fund balance in the Holding Currency with respect to the Contributions shall be made available to the Donors via the World Bank’s Trust Funds Donor Center secure website.

- The Bank shall provide to the Donors via the World Bank’s Trust Fund Donor Center secure website, within six (6) months following the end of each Bank fiscal year, an annual single audit report, comprising (i) a management assertion together with an attestation from the Bank’s external auditors concerning the adequacy of internal control over cash-based financial reporting for all cash-based trust funds as a whole; and (ii) a combined financial statement for all cash-based trust funds together with the Bank’s external auditor’s opinion thereon.  The cost of the single audit shall be borne by the Bank.

- If a Donor wishes to request, on an exceptional basis, a financial statement audit by the Bank’s external auditors of the Trust Fund, the Donor and the Bank shall first consult as to whether such an external audit is necessary.  The Bank and the Donor shall agree on the appropriate scope and terms of reference of such audit.  Following agreement on the scope and terms of reference, the Bank shall arrange for such external audit.  The costs of any such audit, including the internal costs of the Bank with respect to such audit, shall be borne by the requesting Donor.

- The Bank shall make available to the Donors copies of all financial statements and auditors’ reports received by the Bank from Recipients pursuant to any Grant Agreements in accordance with the Bank’s Access to Information Policy.

- The Bank shall provide the Donors with annual reports on the progress of activities financed by the Contributions.  Within six (6) months of the End Disbursement Date (as defined below), the Bank shall furnish to the Donors a final report on the activities financed by the Trust Fund.

- Any Donor may review or evaluate activities financed by the Trust Fund at any time up to six (6) months following the End Disbursement Date.  The Donor and the Bank shall agree on the scope and conduct of such review or evaluation, and the Bank shall provide all relevant information within the limits of the Bank’s applicable policies and procedures.  All associated costs, including any costs incurred by the Bank, shall be borne by the Donor.  It is understood that any such review or evaluation will not constitute a financial, compliance or other audit of the Trust Fund.

Section 3: CDF Grants

- Project Preparation and Approval Process

- World Bank Task Team Leader (TTL) will prepare a Project Concept Note following Bank’s procedures for micro and small grants. These Project Concept Notes may either be based on the short project proposals received under the INTOSAI-Donor Cooperation’s Global Call for Proposals or be based on Bank’s ongoing program and dialogue with the SAI or INTOSAI body. Project Concept Notes are required to be approved by the respective World Bank Country Director to ensure good fit with the Bank’s Country Assistance Strategy/Country Partnership Framework.  The Bank TTL will need to have TF accreditation to task manage the project.

- All PCNs should demonstrate SAI leadership of the initiative, harmonization and alignment of support, coordination with any ongoing initiatives, and focus on delivering results. To ensure effective coordination with in-country donors, PCNs should also disclose details of funding or other support already obtained, as well as details of any outstanding funding requests.

- The Project Concept Note (PCN) template (see Annex 3) will require description of the project purpose, outcomes and outputs, along with performance indicators that are measurable, which may be presented in a logframe format (see Annex 5).

- The TTLs will submit PCNs to the Program Manager, who will review and evaluate proposals according to the approved scoring methodology (See subsection J below) and produce a list ranking each proposal. The PM will submit the scoring and ranking list to the Funding Board for decision.

- The FB will meet, in person or virtually, to review the PCNs submitted by the PM. The FB will (i) approve the project for financing, or (ii) ask the TTL to address identified issues before approving the project, or (iii) reject the proposal for financing. In situations where the FB has approved the PCN and has made some suggestions/comments on the approved PCN, the PM will follow-up with TTLs to ensure that FB comments and suggestions are considered in finalizing the grant agreements. The FB will be kept informed of such changes/developments through six-monthly progress reports or through periodic emails depending upon the severity of the issue. In situations where the FB has identified several issues that need to be addressed before the PCN could be considered, the FB will review the revised PCN before making the funding decision. The total value of proposals approved will be no more than the current value of available resources in the SAI CDF.

- The PM will, on behalf of the Funding Board, provide feedback to the TTL for unsuccessful applications. The PM will publicize the list of successful funding applications through suitable means, within 4 weeks of the finalization of funding decisions.

- Once the Funding Board approves a project, the TTL will work with the Recipient to finalize project preparation and prepare a Grant Agreement for signature by the Recipient and the World Bank. The projects will then be disbursed consistent with the guidelines in the TF Handbook of the World Bank and implemented in accordance with regular Bank specified operational procedures for recipient-executed grant activities. Each project will have a designated project leader from the recipient.

- Criteria for evaluating Project Concept Notes

- The following priorities of the INTOSAI-Donor Cooperation will be duly considered in making the funding decisions: i) Support for SAIs in Low Income and Lower Middle Income countries, ii) Assistance to SAIs in implementing the ISSAIs, iii) Regional and global support, iv)Initiatives that encourage peer-to-peer support, v) Initiatives that encourage south-south cooperation, and vi) Support to Strengthening SAI Independence.

- A transparent scoring system will be used in evaluating project concept notes. All PCNs should demonstrate SAI leadership for the proposed project, harmonization and alignment of donor support, coordination with other ongoing initiatives, and focus on delivering results. The assessment will be carried out by the SAI CDF Program Manager, without any involvement of an INTOSAI body in accordance with paragraph 22 of the INTOSAI-Donor Memorandum of Understanding, which stipulates that INTOSAI will refrain from involvement in any decisions related to funding.

- The evaluation criteria are included in Annex 4.

- Grant Amount, Duration, and Co-financing

- Grants from the SAI CDF to eligible beneficiaries will range from US$250,000 to US$2,000,000 – to be disbursed over a 2-5 year time period. Grant financing should not exceed 20% of grantee’s total organizational budget; but it may cover 100% of proposed interventions.

- Grant Eligible Expenditures

- The Grant Agreements with the recipients will specify the eligible categories of expenditure, such as goods, consulting services, knowledge transfer partnerships, and training.

- Goods: Will be procured in accordance with the Guidelines on “Procurement of Goods, Works, and Non-Consulting Services under IBRD Loans and IDA Credits & Grants by World Bank Borrowers”.

- Consulting services: Will be procured in accordance with the Guidelines on “Selection and Employment of Consultants under IBRD Loans and IDA Credits & Grants by World Bank Borrowers”.

- Knowledge transfer partnerships: Peer-to-peer cooperation partnerships within INTOSAI bodies, e.g. SAI-to-SAI, Regional and INTOSAI Development Initiative capacity development program, can be financed on a justified, actual cost reimbursement basis. Recipients can access a provider of knowledge transfer directly, or through calls to invite potential providers to express interest on the provision of knowledge transfer (for specific assignments or to form a pool of potential partners under a framework agreement).

- Training: Training costs (i.e., other than those involving goods, consulting services and knowledge transfer partnerships) can be financed with due attention to economy and efficiency.

- Grant Agreements

- Entered between the World Bank and each recipient (beneficiary), the Grant Agreements include provisions on the objectives of the grant activities; activities eligible for funding (consistent with the activities approved under the Administration Agreement); the Recipient’s obligations in respect of procurement, contract administration, financial management and auditing, and progress reporting; and disclosure of information. The World Bank designates a Task Team Leader (TTL) to oversee the Recipient’s implementation of project grants in accordance with the grant agreements.

- Grant Project Reporting

- At the project level, the Grant Recipient is responsible for reporting on project progress to the World Bank in accordance with the terms of the Grant Agreement, including reporting on progress against the targets envisioned in the concept note. The World Bank TTL maintains overall responsibility for monitoring and ensuring that the necessary documentation is received.

- Grant agreements require that recipients maintain acceptable financial management systems for Grant funds and normally require that:

- The Recipient provides interim unaudited financial reports in form and substance satisfactory to the World Bank covering such periods as are specified in the agreement.

- The Recipient arranges for an external audit of the financial statements for the project, by independent auditors and in accordance with auditing standards both acceptable to the World Bank, covering such periods as are specified in the agreement.

- The World Bank PM will provide the Funding Board with copies of the financial statements and auditors’ reports received by the World Bank from the Recipients pursuant to the Grant Agreements.

- Grant Implementation Supervision

- The Bank shall be responsible for the supervision of the activities financed under any Grant Agreements.  Subject to the consent of any relevant Recipients, representatives of the Donors may be invited by the Bank to participate in Bank supervision missions related to the Trust Fund.

- The Bank shall promptly inform the Donors of any significant modification to the terms of any Grant Agreements and of any contractual remedies that are exercised by the Bank under any Grant Agreements.  To the extent practicable, the Bank shall afford the Donors the opportunity to exchange views before effecting any such modification or exercising any such remedy.

Section 4: Relationship with the INTOSAI-Donor Cooperation

- The INTOSAI-Donor Cooperation Steering Committee is responsible for issuing Global Calls for Proposals under the umbrella of the Cooperation. Proposals resulting from such Global Calls for Proposals will be an important source of applications for funding from the SAI CDF. The INTOSAI-Donor Secretariat administers the issuing of Global Calls for Proposals, under the guidance of the Steering Committee.

- Upon request, the INTOSAI-Donor Secretariat may perform preliminary review of short project proposals. Upon request, the Secretariat may also provide advice to the SAI CDF Funding Board.  The INTOSAI-Donor Secretariat is responsible for raising awareness of the SAI CDF within the INTOSAI and donor communities.

- INTOSAI regional and sub-regional bodies provide, subject to their available resources, support to applicant SAIs within their regions and take a lead in developing applications for programs of benefit to groups of SAIs within their regions.

- On behalf of the Funding Board, the SAI CDF Program Manager provides a report on the activities of the SAI CDF at the Cooperation Steering Committee meeting.

| LOGFRAME |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PURPOSE STATEMENT | To strengthen governance and public financial management in developing countries, through capacity development support to Supreme Audit Institutions, directly and through INTOSAI global and regional bodies. |  |  |  |  |  |
| OUTCOME | Indicator | Baseline 2012 | Milestone 1 2014 | Milestone 2 2016 | Target 2018 | Assumptions |
| Improved performance of SAIs in developing countries | Percentage of SAIs in developing countries (for which a PEFA assessment is available) scoring a C or higher on PEFA PI-26 ‘Scope, Nature and Follow-up of External Audit’ | LDC & LI = 32% LMI = 43% UMI = 67% | LDC & LI = 35% LMI = 45% UMI = 70% | LDC & LI = 40% LMI = 50% UMI = 80% | LDC & LI = 50% LMI = 60% UMI = 90% |  |
|  |  | Source |  |  |  |  |
|  |  | INTOSAI-Donor Secretariat review of latest indicator scores on the full PEFA database (including unpublished assessments) |  |  |  |  |
|  | Indicator | Baseline 2010 | Milestone 1 2014 | Milestone 2 2016 | Target 2018 |  |
|  | Percentage of SAIs in developing countries that issue their annual audit reports within the established legal time frame | LDC & LI = 55% LMI = 74% UMI = 75% | LDC & LI = 60% LMI = 80% UMI = 80% | LDC & LI = 65% LMI = 85% UMI = 85% | LDC & LI = 75% LMI = 90% UMI = 90% |  |
|  |  | Source |  |  |  |  |
|  |  | INTOSAI stock taking survey |  |  |  |  |
|  | Indicator | Baseline 2012 | Milestone 1 2014 | Milestone 2 2016 | Target 2018 |  |
|  | Percentage of SAIs in developing countries (for which a PEFA assessment is publicly available) in which all external audit reports on central government consolidated operations are made available to the public through appropriate means within six months of completed audit. | LDC & LI = 34% LMI = 63% UMI = 76% | LDC & LI = 40% LMI = 70% UMI = 80% | LDC & LI =50 % LMI = 75% UMI = 85% | LDC & LI = 60% LMI = 80% UMI = 90% |  |
|  |  | Source |  |  |  |  |
|  |  | INTOSAI-Donor Secretariat review of latest published PEFA reports (PEFA PI-10, criteria (iv)) |  |  |  |  |

Annex 1. SAI Capacity Development Fund (SAI CDF) – LOGFRAME

Annex 2: SAI Capacity Development Fund – List of Eligible Beneficiaries

Annex 3. Project Concept Note Template

I. Introduction and Context

A. Country Context

B. Sectoral and Institutional Context (description of the current PFM scenario including ongoing PFM reforms, state of the SAI including SAI Strategy and SAI Capacity Development Plan, links to the legislative scrutiny)

C. Ongoing SAI reforms (including current and previous donor funded projects). Linkage with the proposal, if any, submitted by the SAI under the INTOSAI-Donor Cooperation Secretariat’s Global Call for Proposals should be explained.

D. Relationship to CAS/CPF

II. Project Context

A. Project

1. Description of the Project (also describe how the proposed project fits into the overall SAI Strategy and SAI Capacity Development Plan)

2. Project Development Objective(s)

3. Detailed Project Components and Costs (including assumptions) and Financing (including contribution from the SAI)

4. Key Results – Outcomes, Outputs

5. Key Risks (SORT) and Issues including risk mitigation measures

6. Monitoring Framework including indicators, baseline, targets, and monitoring mechanisms (use logframe)

B. Implementing Agency Assessment

Annex 4: Criteria for the Evaluation of Project Concept Notes

- The following scoring system will be used to evaluate Project Concept Notes for funding under the SAI Capacity Development Fund (SAI CDF).

- The assessment will be carried out by the SAI CDF Program Manager, without involvement of any INTOSAI body in accordance with paragraph 22 of the INTOSAI-Donor Memorandum of Understanding, which stipulates that INTOSAI will refrain from involvement in any decisions related to funding.

- Project Concept Note will be given a score against each of the evaluation criteria included the following table – maximum score for each evaluation criteria is 10.

| No. | Criteria | Max Score | Actual Score |
| --- | --- | --- | --- |
|  | Country Ownership and Leadership |  |  |
| 1 | SAI involvement in the design of the project | 10 |  |
|  | Strategy and Project Design |  |  |
| 2 | The project activities clearly fits into the long term capacity development strategy of the SAI | 10 |  |
| 3 | Project activities clearly links to the identified needs | 10 |  |
| 4 | Project activities and proposed project budget are necessary and sufficient to achieve expected outcomes and outputs | 10 |  |
| 5 | There is clear and logical sequence of activities to achieve project objectives | 10 |  |
|  | Alignment and Coordination |  |  |
| 6 | PCN clearly identifies links to and builds on previous and ongoing projects | 10 |  |
|  | Results Framework |  |  |
| 7 | A monitoring framework is proposed (including indicators, baseline, targets, and monitoring mechanisms) | 10 |  |
|  | Sustainability |  |  |
| 8 | PCN clearly articulates risks to achieving the PDO | 10 |  |
| 9 | PCN clearly articulates risk mitigation measures to address the identified risks | 10 |  |
| 10 | Results from the proposed project are sustainable after the completion of the project | 10 |  |
|  | Total | 100 |  |

Annex 5: Project Concept Note – Logframe Template

| LOGFRAME | PROJECT TITLE: APPLICANT: LEGAL APPLICANT: IMPLEMENTING PARTNER(S): |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PURPOSE STATEMENT |  |  |  |  |  |  |
| OUTCOME | Indicator | Baseline + yr | Milestone 1 + yr | Milestone 2 + yr | Target + yr | Assumptions |
|  |  | Source |  |  |  |  |
|  | Indicator | Baseline + yr | Milestone 1 + yr | Milestone 2 + yr | Target + yr |  |
|  |  | Source |  |  |  |  |
|  | Indicator | Baseline + yr | Milestone 1 + yr | Milestone 2 + yr | Target + yr |  |
|  |  | Source |  |  |  |  |
| TOTAL INPUTS ($) | SAI CDF ($) | Govt ($) | Other ($) | Total ($) | SAI CDF SHARE (%) |  |

Annex 5: Project Concept Note – Logframe Template (continued)

| OUTPUT 1 | Indicator | Baseline + yr | Milestone 1 + yr | Milestone 2 + yr | Target + yr | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Source |  |  |  |  |
|  | Indicator | Baseline + yr | Milestone 1 + yr | Milestone 2 + yr | Target + yr |  |
|  |  | Source |  |  |  |  |
| INPUTS ($) (OUTPUT 1) | SAI CDF ($) | Govt ($) | Other ($) | Total ($) | SAI CDF SHARE (%) |  |
| OUTPUT 2 | Indicator | Baseline + yr | Milestone 1 + yr | Milestone 2 + yr | Target + yr | Assumptions |
|  |  | Source |  |  |  |  |
|  | Indicator | Baseline + yr | Milestone 1 + yr | Milestone 2 + yr | Target + yr |  |
|  |  | Source |  |  |  |  |
| INPUTS ($) (OUTPUT 2) | SAI CDF ($) | Govt ($) | Other ($) | Total ($) | SAI CDF SHARE (%) |  |

Relevant documentation of the INTOSAI-Donor Cooperation can be found in www.idi.no.

The Task Force was comprised of the INTOSAI-Donor Cooperation Secretariat (IDI), African Development Bank, Belgium, Canada, EU, Ireland, Switzerland, USA, UK and the World Bank. Participants at the February 2012 meeting of the Task Force included the Asian Development Bank, Australia, Austria, Denmark, and Norway.

At present Cuba, Democratic Republic of Korea and Nauru are not IBRD members. Arrangements for the Palestinian Administered Areas remain to be confirmed.

Where an eligible beneficiary is not a legal entity (e.g. INTOSAI committees, sub-committees, working groups and task forces), applications must be made by a legal entity acting on behalf of the beneficiary.

Programmatic Trust Funds finance multiple grants under a two-stage mechanism. In the first stage, one or more donors agree to a broad thematic framework designed to support a program of activities over multiple years, and the donor(s) commit(s) funds. In the second stage, the grants are approved for specific projects or activities.

The Administrative Agent will issue a Call of Funds to the signatories on a periodic basis, according to the schedule agreed in the Administration Agreement. Under World Bank-administered TFs, the Bank invests and reinvests the contributions pending their disbursement in accordance with its policies and procedures. In MDTFs, the Bank credits all income from such investments to the TF to be used for the same purposes as the contributions.

Direct earmarking can be accommodated under Single-Donor trust funds, which could potentially support the same overall program and share harmonized governance arrangements.

Per the Framework Agreement between the EC and the World Bank, it is possible for the EU to contribute to a MDTF using a notional approach to fulfill EU requirements. Under this approach, the EU requirements are met as long as the amount contributed by other donors to the MDTF is sufficient to pay for the activities (i.e. component of the trust fund) which are ineligible for the EU or, in the case of end disbursement date requirements, as long as the amount disbursed from the trust fund prior to the end disbursement date for the use of the EU contribution is at least equal to the amount of the EU's contribution to the trust fund.

This relates to non-program specific activities, such as processing and administering TFs, provision of financial management, maintenance of information systems and financial reporting.

This relates to program-specific activities at the Administration Agreement level, such as work program planning, appraising and monitoring implementation of activities, communications and outreach, coordinating with donors and program reporting.

This includes project supervision activities at the Grant Agreement level, such as implementation support, confirmation of project progress, procurement and financial management supervision.

Short project proposal templates and guidance for the global call for proposals is made available publicly by the INTOSAI-Donor Cooperation Secretariat.

For instance, national competitive bidding (NCB) could be used where foreign bidders are not expected to be interested (per the conditions established in the Guidelines), and the shopping method could be used for small value contracts (below US$100,000 equivalent) for off-the-shelf goods.

For example, simplified procedures established in the Guidelines could be used for assignments below US$300,000 equivalent.

For instance, following the Recipient’s own procedures such as reimbursement against statements of expenditures based on a prior approved budget.

For small operations (not exceeding $500,000) financed by World Bank-administered TFs, flexible financial management arrangements can apply, such as an exemption from the annual audit requirement where alternative mechanisms exist, which provide equivalent assurance on the use of funds; or the possibility of a single audit to be conducted at the completion of project activities, if the implementation period is not expected to exceed 24 months.

Classification based on OECD-DAC classification effective for reporting on 2011, 2012 and 2013 flows. LDC = least developed countries. LI = other low income countries. LMI = lower middle income countries. UMI = upper middle income countries.

Indicators at the outcome level are used for monitoring the overall performance improvement of SAIs. Such high level performance changes are the result of all forms of SAI capacity development and cannot be attributed solely to the SAI Capacity Development Fund.